Annexure ‘E’

PROGRESS OF CONSTRUCTION WORKS & CONVERSION PROJECTS

PROGRESS OF MAJOR WORKS (Works costing more than 5 crores) March, 2017

(Figures in crore of Rs.)

| S N | Category | Detail of works | PB Item No. (16-17) | Year of sanction | Anti. Cost | Exp. up to Mar.,16 | Current year | Physical progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Final Modification Estimate 2016-17 | Exp. |  |  |
|  | New Line | Dausa – Gangapurcity (92.67 km) | 1 | 1996-97 | 780.98 | 310.70 | 26.88 | 28.27 | 90% 66% | Dausa-Deedwana (35.44 km) section Earthwork, blanketing, Ballast supply, major bridges & minor bridges completed. 37.90 Km track linking has been completed in the section. Station buildings (4) - Up to roof level completed on 2 stations. Tender for Flash butt Welding (6,400) - Contract awarded on 16.11.2016, work is in progress. For ROB (1 no.), Railway Span: Completed except crash barrier & expansion joint, finishing work. Approaches: Work is in progress. 12 LHS have been completed out of 14 so far. For Platform shelters, water supply, and road approaches and other passenger amenities, Contract awarded on 16.11.2016. For P way/track works, contract awarded on 06.12.16. This project is targeted to complete by June, 2017. Deedwana-Gangapur city (57.23 km) section Earthwork done during the month – Nil, cumulative progress – 21,62,000 cum out of total 22,22,000 cum. Blanketing done during the month – Nil, cumulative progress – 2,03,500 cum out of total 3, 05,000 cum. Minor bridges completed during the month – Nil, cumulative progress – 26 out of total 40. All major bridges completed. Tunnelling work done during the month – Nil, cumulative progress - 997 metres out of 2,120 metres length. Work terminated on 07.07.2015. Contract for balance work awarded on 23.09.2016. Revised estimate sanctioned by Railway Board vide letter No. 2000/W-1/NL/WR/1 dt. 07.03.2017. |
|  | New Line | Ratlam-Dungarpur Via. Banswara (189.00 km) New line project | 3 | 2011-12 | 2417.24 | 71.31 + 45.74 EBR | 58.57 | 59.81 | 6.25% | Tender for earth work between Km 142.82 to 163.00 and Km 163 to 184.6 awarded on 07.09.15 & 6.11.15 respectively. Earthwork done during the month – 85,500 Cum, cumulative progress – 66,88,800 cum out of total 3,05,87,000 cum. Minor bridges completed during the month – Nil, cumulative progress – 08 out of total 414. Contract for 91 minor bridges and 23 RUBs at a cost of Rs. 118.11 cr. (from km 0 to 17, 106-123 and 142.85 to 163) awarded on 04.04.14 and 18.12.2014. Total 933 cheques distributed out of 1277 for land awards (350 out of 409 of Dungarpur, 251 out of 305 of Banswara and 332 out of 563 of Ratlam). Work in progress in 34 km stretch where land made available. Part Detailed estimate (Part-II) of Dungarpur-Ratlam via. Banswara new line (191.80 km) of Rs. 2417.24 cr. (Civil - Rs. 2373.20 cr., S&T - Rs. 3.65 cr. and Electrical - Rs. 40.39 cr.) sanctioned by Rly. Bd. vide letter No. 2011/W-I/NWR/NL/20 Estimate dt. 19.10.2015. Contract for works, (Rs. 349 crore), where land is available, have been awarded & works are in progress. Govt. of Rajasthan has put land acquisition for the project on hold and is not paying for the compensation when award have already been declared. Villagers have stopped the railway work form 11.01.2016 for want of balance compensation of land. Rajasthan Govt. has expressed inability to share the cost of project, therefore Railway Board, vide letter No. 2011/WI/NWR/NL/20 dt. 22.03.20174, has decided to freeze the project and stop the construction activities on the project on as-is basis. |
|  | New Line | Thiyat Hamira - Sanu (58.5 km) | 4 | 2013-14 | 262.46 | 3.35 | 52.55 | 68.43 | 20% | Work sanctioned in 2013-14. RSMML deposited Rs. 118.46 cr. with Rly. on 23.05.2013 towards their share of cost. Detailed Estimate costing Rs. 262.46 cr. sanction by GM/NWR on 08.07.2015. Sanction Letter No. NWR/HQ/ S&C/444283904 dt. 08.7.2015. Integrated contract of Civil & Electrical work costing Rs. 117.34 cr. awarded on 23.03.2016. The mobilization of machineries, manpower and other establishment started at site. 1564.19 Bigha (253.46 Hect.) (Govt. land) State authority accorded approval for allotment vide letter, dated 29.02.2016. Cost of land was paid to State on 15.03.2016. Office order was issued by DM/Jaisalmer on 12.05.16. Total land physically handed over to Railways and all land plans are signed jointly. Mutation of 55Hect. Land got done. 199.14 Bigha (32.28 Hect.) (Department Land + Gochar land) – State authority accorded approval for allotment of land vide letter, dated 03.06.2016. Cost of land was paid to State Authority on 28.07.2016. Office order issued on 08.07.2016. Land physically handed over to Railways and land plans are already signed jointly. 235.04 Bigha (38.07 Hect.) (Private Land) The calculation for amount of compensation for private land (38.07 Hect.) has been got completed by nominated committee and submitted to the land acquisition officer (i.e. SDM). Notification of Section 19 published in Newspaper on 18.02.2016. Hearing done by land acquisition officer on 21/22.03.2016. Committee nominated by land acquisition officer in March'16 Joint survey by nominated committee is completed in June '16, The award of compensation for Private Land (38.07 Hect.) has been got approved by Minister level (Government of Rajasthan). Demand note raised by Land Acquisition Officer & same paid on 23.02.2017. 9.17 Bigha (42.06 Hect.) (Forest Land) The proposal has been forwarded to Government of India, Regional Office, Lucknow by Government of Rajasthan with approval of Minister of Forest. Approval for allotment of equivalent non-forest land obtained on 08.07.2016. Payment made to State Authority on 30.08.16. Office order for compensatory land issued by DM office on 29.07.2016. REC meeting held on 05.01.17 at Regional Office, Lucknow and stage-I approval obtained. Earthwork done during the month – 1,23,000 Cum, cumulative progress – 11,01,000 cum out of total 27,50,000 cum. Minor bridges completed during the month 3, cumulative progress - 11 out of total 50. Ballast supply completed during the month is 1,683, cumulative progress is 1,883 cum out of 1,67,500 cum. |
|  | New Line | Ajmer-Kota (Nasirabad-Jalindri) (145 km) | 5 | 2013-14 | 822.00 | 0 | 0 | 0 | - | Work sanctioned in 2013-14. Cost Rs. 822.00 cr. & ROR (-) 6.61%. CCEA sanction yet to be obtained by Railway Board. |
|  | New Line | Pushkar - Merta (59 km) | 6 | 2013-14 | 323.00 | 0 | 0 | 0 | - | Work sanctioned in year 2013-14. Cost Rs. 323.00 cr. & ROR (-) 7.65%. CCEA sanction yet to be obtained by Railway Board. |
|  | New Line | Ajmer (Nasirabad) - Sawai Madhopur (Chauth ka Barwara) via Tonk (165 km) | 7 | 2015-16 | 873.71 | 0 | 0 | 0 | - | Work sanctioned in year 2015-16. Cost Rs. 873.71 cr. & ROR (-) 7.25%. Cabinet Committee on Economic Affairs (CCEA) have approved on 22.2.14 (ref. Rly. Bd's letter No. 2010/W-I/NWR/NL/8 Survey/Pt-I dt. 12.08.2015). Project sanctioned with 50% share of cost and provision of free land by Govt. of Rajasthan. Consent for entering MOU awaited from State Govt. of Rajasthan. State Govt of Rajasthan advised vide letter dt. 12.05.16, 09.06.16 & 04.08.16. Contract for FLS work finalised on 28.03.2016 and work is in progress. Rajasthan Govt. has refused to share the cost of project. |
|  | Gauge Conversion | Ajmer-Chittaurgarh-Udaipur (300 km), incl. Material Modifications for extension from Udaipur to Umra (11 km), Mavli- Nathdwara (16 km), Mavli Jn.-Bari Sadri (82.01 km) and Natdwara-New Nathdwara (10.8 km) new line. | 8 | 1996-97 | 855.16 | 557.16 | 17.11 | 23.66 | 100% 100% -- 9% | Ajmer-Chittaurgarh-Udaipur (300 km):- Work completed & section opened. Mavli-Nathdwara MM (16.00 Km):- CRS inspection done on 14.04.2011 and authorization for running of passenger trains at 100 Kmph issued on 15.04.2011. Section commissioned in 2011-12. Natdwara-New Nathdwara new line (10.8 km): - FLS completed. Mavli Jn.-Bari Sadri MM (82.01 km):- Work sanctioned in 2013-14. Field survey has been completed. Detailed Estimate costing Rs. 290.66 Cr. sanctioned by Railway Board on 27.11.2015. Preparation of L-section is in progress. Contract amounting to Rs. 137.40 Cr. awarded on 16.06.2016. Earthwork done during the month – 81,000 Cum, cumulative progress – 3,34,000 cum out of total 22,75,000 cum. Minor bridges completed during the month 16, cumulative progress - 42 out of total 124. Ballast supply completed during the month is 410 cum cumulative progress is 1,780 cum out of 1,60,000 cum. Contract of FB welding awarded on 20.02.2017. Section has been closed from 01.11.2016 for taking up GC work. |
|  | Gauge Conversion | Jaipur-Ringus-Churu & Sikar-Loharu (320.04 km) | 10 | 2008-09 | 658.07 | 428.57 | 114.99 | 118.39 | 100% 40% 66% | Sikar-Loharu (122.13 km) section Section commissioned on 01.9.2015 and handed over to Open Line on 24.10.2015. Jaipur-Ringus-Sikar (107.45km) section Tender for earthwork in embankment, cutting etc. and construction/alteration of service building, PF shelter, FOB etc. awarded on 17.11.2015 and work is in progress. Earthwork done during the month – 50,000 Cum cumulative progress – 1,70,000 cum out of total 3,65,000 cum. Ballast supply completed during the month is 5,000 cum cumulative progress is 99,196 cum out of 2,45,000 cum. Tender for major and minor bridges awarded on 17.11.2015 and work is in progress. Track linking completed during the month is 7.60 km, cumulative progress is 15.20 km out of 130 km. Tender for 44 UM & 8 Manned LHS awarded on 23.03.2016. 329 LHSs segment casted. Contract for Ringus - Detour alignment awarded on 24.06.2016. Land acquisition & Earthwork is in progress. Section has been closed from 15.11.2016 for taking up GC work. Fatehpur-Shekhawati-Churu (43.40 km) is targeted to complete by July, 2017. Sikar-Churu section (90.46 km) (Target - 90.46 km commissioning in 2016-17) CRS inspection of Sikar-Fatehpur Shekhawati (47.06 km) section of Jaipur-Ringus-Churu & Sikar-Loharu (320 km) Gauge conversion project has been done on 25.03.17 to 26.03.2017. CRS has authorised section for running of passenger trains at 100 kmph on 27.3.2017. Earth work completed during the month is 10,000 cum, cumulative progress is 4,00,000 cum out of 4,50,000 cum. All 15 Minor bridges completed. Ballast supply completed during the month is 5,000 cum, cumulative progress is 2,35,000 cum out of 2,62,500 cum. Track linking completed. All 04 station buildings completed. All 245 LHS Box segments casted. |
|  | Gauge Conversion | Ratangarh-Sardarsahar (46.75 km) MM of Sadulpur-Bikaner & Ratangarh-Degana (348 km) | 12 | 2007-08 | 872.22 | 796.25 | 14.48 | 15.80 | 90% (RTGH-SRDR) | CRS inspection of Ratangarh-Sardarsahar (46.75 km) GC has been done on 08.3.17 to 09.3.17. CRS has authorised section for running of passenger trains at 75 kmph on 09.3.2017. |
|  | Gauge Conversion | Himmatnagar-Udaipur (208.48 km) | WR-11 | 2008-09 | 829.74 | 188.13 | 127.30 | 132.29 | 55% | The section has been blocked w.e.f. 01.01.2017, for gauge conversion. Earthwork done during the month – 1,07,000 cum, cumulative progress – 48,86,000 cum out of total 71,00,000 cum. Minor bridges completed during the month 11, cumulative progress - 335 out of total 666. Major bridges completed during the month - 03, cumulative progress - 29 out of total 38. Concreting completed during the month is 5,338 cum cumulative progress is 1,86,104 cum out of 3,74,300 cum. Ballast supply completed during the month is 16,500 cum cumulative progress is 38,500 cum out of 4,88,000 cum. 47 LHSs completed. 47 LCs closed. Note :- Out of total project length 299.20 km, NWR is executing 208.48 km GC work. 65 km of NWR portion falls in Gujarat State. Balance GC work of this project is being executed by Western Railway. |
|  | Doubling | Ajmer-Bangurgram doubling (48.43 km) | 21 | 2011-12 | 218.39 | 27.54 | 26.05 | 31.10 | 20% | Work sanctioned in the year 2011-12. Detailed estimate sanctioned by Railway Board amounting to Rs. 218.39 cr. (Rs. 174.62 cr. Civil, Rs. 8.04 cr. Elect. Engg. and Rs. 35.73 cr. S&T) vide letter No. 2011/W-I/NWR/DL/23 Estimate dt. 21.9.2012. Composite contract costing Rs. 113.38 cr. awarded on 24.06.2016. Earthwork done during the month – 13,800 cum, cumulative progress – 61,600 cum out of total 4,50,000 cum. Ballast supply completed during the month is 5,860 cum cumulative progress is 6,585 cum out of 2,00,000 cum. Minor bridges completed during the month 06, cumulative progress - 27 out of total 63. |
|  | Doubling | Guriya-Marwar (43.50 km) & Karjoda-Palanpur (5.40 km) doubling (48.90 km) | 22 | 2011-12 | 206.22 (Rly. portion) | 120.70 | 47.30 | 49.43 | 95% | Sojat-Marwar (21 km) part of Guriya-Marwar (43.50 km) doubling project commissioned on 11.02.2017. CRS inspection of Sojat-Guriya (22.64 km) part of Guriya-Marwar (43.50 km) doubling project has been done on 07.03.2017, authorisation received on 9.03.2017 at 100 kmph. |
|  | Doubling | Bangurgram - Guriya - Patch doubling (47 km) | 24 | 2012-13 | 348.55 | 4.76 | 5.87 | 8.12 | - | Work sanctioned in the year 2012-13 Work for final location survey & drawing work has been completed. Detailed estimate of Rs. 348.55 Cr. has been sanctioned by competent authority (AGM) vide letter No. NWR/HQ/S&C/444283904 on 25.04.2016. Composite contract amounting to Rs. 174.00 Cr. awarded on 11.11.2016. Earthwork done during the month – 41,000 cum, cumulative progress – 61,000 cum out of total 15,00,000 cum. |
|  | Doubling | Rani - Marwar Jn.- Patch doubling (54.50 km) | 25 | 2012-13 | 335.53 | 36.92 | 82.58 | 98.55 | 25% | Work sanctioned in the year 2012-13 Detailed estimate of Rs. 335.53 Cr. sanctioned by Railway Board vide letter No. 2013/W-1/NWR/DL/6 Estimate dt. 14.10.2014. Integrated Tender of Civil & Electrical works of amounting to Rs. 152.62 Cr. is accepted on 30.12.2015. Works are in progress. Earthwork done during the month – 33,000 cum, cumulative progress – 5,33,000 cum out of total 7,00,000 cum. Minor bridges completed during the month 11, cumulative progress - 33 out of total 36. Ballast supply completed during the month is 11,000 cum cumulative progress is 32,000 cum out of 1,89,000 cum. |
|  | Doubling | Alwar-Bandikui (60.37 km) | 26 | 2013-14 | 281.03 | 1.11 | 43.03 | 46.55 | 20% | Work sanctioned in the year 2013-14. Detailed Estimate of Rs. 281.03 cr. (Civil Engg. = Rs. 241.01, S&T Engg. = Rs. 33.26 cr. and Electrical Engg. = Rs. 6.76 cr.) sanctioned by Railway Board vide letter No. 2014/W-I/NWR/DL/19 Estimate dt. 08.09.2015. Contract amounting to Rs. 118.24 Cr. awarded on 18.05.2016. Contractor started mobilisation. Earthwork done during the month – 15,000 cum cumulative progress – 1,88,000 cum out of total 3,00,000 cum. Minor bridges completed during the month 8, cumulative progress - 38 out of total 97. Ballast supply completed during the month is 17,600 cum; cumulative progress is 74,000 cum out of 1,76,000 cum. |
|  | Doubling | Phulera-Digana (108 km) | 27 | 2015-16 | 611.53 | 0 | 0 | 0.005 | - | Work sanctioned in year 2015-16. Detailed Estimate of Rs. 611.53 Cr. sanctioned by Railway Board vide No. 2015/WI/NWR/DL/DPR 2015-16/18 dt. 28.01.2016. The project has been notified in Central Gazette as Special Railway Project. Competent authority for land acquisition is nominated by State Govt. and same is notified in Central Gazette. Section 20(A) (I) notification for land acquisition is issued on 12.05.2016. EPC tender planning is in progress. Concept plan of all yards finalised and got approved from JU/JP division and under approval of HQ. 7 representations received in Private Land Acquisition & all have been replied to ADM/Didwana on dated 14.07.2016. A joint meeting with ADM/Didwana was held on 16.08.2016 for disposal objection of private land owners. A joint meeting with DM/Nagour was held on dated 17.09.2016 at Parbatsar City to expedite the process for land acquisition regarding land of Sambhar Salt lake. Draft notification under Article 20(E) sent to ADM/Didwana for approval on 17.09.2016. Proposal for Govt. land sent to ADM/Didwana after verification of concern SDM. RFQ NIT was opened on 31.01.2017 & TC minutes accepted on 21.03.2017, finalisation of RFP documents are under progress. |
|  | Works under capital investment programme 2016-17 | Jaisalmer-Bhaber (339 km) new line | - | 2015-16 | 5000.00 | - | - | - | - | Work sanctioned in current year i.e. 2016-17. MOU with Rajasthan Government yet to be signed for creation of SPV for the project. |
|  | Works under capital investment programme 2016-17 | Parbatsar-Kishangarh (45 km) new line | - | 2015-16 | 900.00 | - | - | - | - | Work sanctioned in current year i.e. 2016-17. MOU with Rajasthan Government yet to be signed for creation of SPV for the project. |