## ALl
Position of Estimate under CAO(Con)/GRC
Sl. No. | PB item 11-12 | Description of works | Cost (` in cr.) | Cumulative expenditure (Rs. in cr.) | Status of estimate (As on 11.06.2012)
11 New Lines
1 | 1 | Howrah - Amta - Champadanga | 154.3 | 2.98 | Detailed Estimate No. 727W/1979 of `31.42 crore sanctioned on 02.02.1984. Revised estimate no. 1222W/2000 sanctioned on 31.07.2001.
HQ
| MM | Amta- Bagnan (16 Km) & TAK- Champadanga (8 Km) | 141.9346 |  | Detailed Estimate No.1420W/2009 of `141.93 crore sanctioned on13.10.2009. | HQ
2 | 2 | Bowaichandi - Arambagh | 267.37 |  | Detailed estimate no.1463W/2010 of ` 267.37 Cr sanctioned by Railway Board vide letter no. 2010/W -2/SER/NL/14 dated 09.02.2011.
3 | 3 | Digha - Jaleshwar | 255.11 |  | Part estimate(1446W/2010) for preliminary works for ` 2,07,90,643/- sanctioned by CAO/C/GRC. Detailed estimate no.1469W/2010 of Rs 362,57,02,860/- sent to Board on 03.12.2010. Board raised certain observation vide letter no. 2010/W-2/SER/NL/18 dated 11.03.2011 which has been complied on 18.05.2011. Board again raised certain observation vide letter no. 2010/W-2/SER/NL/18 dated 15.07.2011 which has been complied vide this office letter dated 19.08.2011. Board again raised certain observation vide letter no. 2010/W-2/SER/NL/18 dated 19.10.2011 which has been complied vide this office letter dated 25.11.2011. Comparative statement recast with MM Digha - Egra prepared and submitted to Board on 19.01.2012. Board again asked comprative statement as already submitted vide letter dated 30/3/12. .The same has been complied vide this office letter dated 3/4/12.
|  | MM fo Digha - Egra | 298.52 |  | MM no. 1487W/2011 sanctioned by Rly Board vide letter No 2011/W-2/SER/NL/11 dated 31.05.2011.
4 | ER | Bishnupur Yard in connection with TAK - VSU new line. |  |  | Vetted estimate submitted to CAO/C/E.Railway on 24.01.2011 for taking further necessary action.
5 | 4 | Tamluk - Digha | 293.97 | 1 | Abstract Estimate No. 957W/1986 of `72.91 crore sanctioned on 17.02.1988. Detailed estimate no.1211W/99 sanctioned on 20.04.2000. | HQ
|  | MM for Kanthi - Egra | 247.28 |  | MM Estimate no. 1488W/2011 sanctioned by Rly Board vide letter no. 2011/W-2/SER/NL/14 dated 29.07.2011.
|  | MM for Jangipara - Furfura sharif | 97.23 |  | MM Estimate no. 1486W/2011 sanctioned by Rly Board vide letter no. 201/W-2/SER/NL/13 dated 29.07.2011.
| MM | Deshpran - Nandigram ( 18.5 Km) | 121.4375 |  | Detailed Estiamte No. 1418W/2009 of ` 121.44 crore sanctioned on 16.10.1984. | HQ
| MM | OHE for Deshpran - Nandigram ( 18.50 Km) | 8.259 |  | Detailed Estimate No. 1461W/2010 of ` 8.26 crore sent to Board on 16.10.2010. | HQ
6 | 5 | Bhadutola-Jhargram via Lalgarh (2011-12) | 269.64 |  | Part estimate bearing No 1522W/2011 of ` 2.68 Cr sanctioned on 20.06.2011.
14 Gauge Conversion
7 | 6 | RNC-LAD-TORI |  |  | Detailed Estimate bearing No. 1185W/1997 of `185.31 crore and Std. III interlocking Estiamte No. 1249W/2002 of `8,76,23,020/- sanctioned on 13.09.2000 & 29.05.03 respectively. Pending for Electrical and S&T sub-estimate. Third reminder sent on 03.02.2012.
8 | 7 | Rupsa - Bangriposi | 137.56 & 328.24 | 40 | Detailed estimate no.1244W/2002 for ROP - BPO costing to ` 50.54 Cr. & detailed estimate 1326W/2006 for BPO-BGY costing to ` 87.02 sanctioned on 29.04.03 & on 29.09.06 respectively. MM Estimate for ROP-Buramara & Chakulia bearing no. 1369W/2008 of ` 328.24 crores sanctioned. MM estimate bearing no 1444W/2010 of `39,40,506/- for S&T works in between BPO-BGY sent to Board for sanction on 11.05.2010.
9 | 8 | BDR |  |  | Detailed Estimate No. 1219W/2000 for BDR of `111.90 crore(G) sanctioned on 11.01.2001. Detailed Estimate No. 1233W/2001 for RNGR-MSAE of `46,25,52,910/- sanctioned on 05.09.02. Part detailed estimate No. 1293W/2004 of `38.92 crore for Bowaichandi - Khana sanctioned by Board. Detailed Estimate of Bankura - Mukutmonipur No. 1295W/2004 of `85.63 crore sanctioned.
|  | Mukutmonpur - Uparsol (26.7 Km) | 211.51 |  | MM estimate no. 1491W/2011 sanctioned by Rly Board vide letter no. 2011/W-2/SER/NL/12 dated 29.07.2011.
|  | Bankura - Purulia via Hura | 294.89 |  | MM estimate no. 1497W/2011 sanctioned by Rly Board vide letter no. 2011/W-2/SER/NL/27 dated 27.07.2011.
15 Doubling
10 | 9 | PDPH-BSPX Doubling | 129.74 | 70 | Estimate no.1332W/2006 sanctioned on 04.01.2007. Pending for Civil & Electrical sub-estimate. 3rd reminder sent on 31.01.2012.
11 | 10 | Banspani - Jaruli(9 Km) | 90.9 | 4 | Detailed estimate no. 1371W/2008 sanctioned on 07.08.2008.
12 | 11 | BBN - BJMD | 50.01 | 40 | Estimate no.1350W/2007 sanctioned on 24.09.2007. Material Modification Estimate No.1437W/2009 cost of `1,48,94,336/- sanctioned by GM. 2nd Material Modification Estimate No.1458W/2010 cost of ` 99,84,094/- sanctioned by GM
13 | 12 | GKL - MDN new Br. (Br. No. 143) | 34.15 | 15 | Estimate no.1358W/2007 sanctioned on 17.04.08. Revised estimate sent finance for vetting on 21.09.2011. Finance made observation vide letter dt. 29.09.2011 which is under compliance. Estimate resubmitted to finance for vetting on 24.01.2012.
14 | 13 | BUF - DMF(DMF to CJG) | 99 | 50 | Estimate no.1356W/2007 sanctioned on 03.03.08. Revises estimate bearing no. 1525W/2011 costing ` 132.87 Cr. under finance vetting. Finance raised observation vide letter dated 30.09.2011 which is under compliance. Revised estimate resuubmitted to finance for vetting on 24.01.2012.
15 | 14 | RKSN - SINI - 3rd line | 91.61 | 2 | Detailed Estimate No. 1370W/2008 sanctioned on 20.08.2008.
16 | DW | PKU-HLZ (Phase-I) doubling. |  |  | Detailed Estimate No. 1226W/2000 of `26.97 crore sanctioned by Board on 14.12.2001As the expenditure exceeded more than 25% of sanctioned cost, Dy.CE/C/KGP was asked to submit revised estimate in the year 2006. But inspite of several reminders, no estimate has been submitted by him.
17 | 15 | Panskura - Ghatal | 276.69 |  | MM estimate no. 1489W/2011 of sanction proejct of Panskura - Kharagpur submitted to Rly Board on 02.02.2011. Board asked to submit estimate after conducting FLS. Accordingly, Part estimate bearing No 1523W/2011 of ` 2.86 Cr sanctioned, vide letter No PD/W/548/1/2706 dated 12.07.2011, by CAO/C/GRC .
18 | 17 | ADA-JOC | 25.31 | 15 | Estimate no.1355W/2007 sanctioned on 07.03.08. Pending for Civil & Electrical sub-estimate. 2nd reminder sent on 03.02.2012.
19 | 18 | Champajharan - Bimalgarh | 177.38 |  | Part estimate(1449W/2010) of Rs2,06,58,167/-sanctioned by CAO(C )GRC. Detailed Estimate No. 1472W/2010 of ` 177.38 Crores sanctioned by Board on 28.04.2011.
20 | 21 | Muri-Muri North Cabin | 17.22 | 2 | Detailed Estimate No. 1375W/2008 sanctioned on 12.09.2008.
21 | 22 | Dongaposi- RKSN - 3rd line | 309.44 |  | Part estimate(1448W/2010) of `44,04,865/- sanctioned by CAO/C/GRC. Detailed estimate(1481W/2010) of ` 388.67 crore sanctioned by Railway Board.
22 | 23 | TPKR - SRC 4th line | 46.79 | 20 | Estimate no.1283W/2004 sanctioned on 17.02.2006.
23 | 24 | SINI - Adityapur - 3rd line | 143.16 |  | Part estimate(1450W/2010) of `82,94,657/-sanctioned by CAO(C )GRC. Detailed estimate bearing no 1465W/2010 costing `143,15,76,280/- sanctioned by GM on 29.11.2010.
24 | 25 | Bhojudih - Mohuda (2011-12) | 134.19 |  | Part estimate bearing No 1516W/2011 of ` 81,66,932/- sanctioned vide letter No PD/W/770/1912 dated 18.05.2011.
25 | 26 | Kharagpur to Gokulpur via Girimaidan (2011-12) |  |  | Detailed estimate bearing no. 1514W/2011 of ` 42.24 Crore sanctioend by CAO/C/GRC vide this office letter no.PD/W/763/3273 dt. 19.08.2011.
26 | 27 | 3rd line from Rajkharswan to Chakradharpur (20 Km) with OHE (12-13).ROR: 21.88%, (CAP) |  |  | Part estimate bearing no. 1546 W/2012 of ` 1.82 crores vetted by finance.
27 | 28 | Doubling from Andul (Fly over) to Baltikuri (7.25 Km)) with OHE (12-13), ROR: 15.76%, (CAP) |  |  | Detailed estimate is under preparation.
28 | 29 | 3rd line from Monoharpur to Bandamunda (30 Km) with OHE (12-13), (CAP) |  |  | Being processed for transfer to RVNL.
29 | 30 | 3rd line from Kharagpur to Narayangarh (23 Km) with OHE (12-13), ROR: 16.46%, (CAP) |  |  | Part estimate bearing no. 1548W/2012 of ` 0.87 crore sanctioned by CAO/C/GRC vide letter no .PD/W/77/1891 dated 8/5/12.
16 Traffic Facility
30 | 31 | Santragachi - Island platform (2011-12) | 7.94 |  | Detailed estimate 1529W/2011 costing ` 11,55,98,811/- sanctioned by CE/C/HQ/GRC vide this office letter no.PD/W/784/0021 dated 02.01.2012.
31 | 32 | TATA - ADTP Yard remodelling | 39.82 | 14.15 | For ADTP yard Estimate no.1323W/2006 costing `13.71 Cr. sanctioned on 30.11.06 & for Tatanagar yard, Estimate no.1340W/2006 costing `26.11 Cr. sanctioned on 22.03.2007. Due to increase in cost Revised estimate vetted by finance.
32 | 37 | BBN - Yard remodelling | 8.77 | 1.49 | Detailed Estimate no.1359W/2007 sanctioned by Board on 01.04.2008.
33 | 39 | KLG - Full length siding | 5.42 | 0.01 | Detailed Estimate no.1352W/2007 costing `5,41,69,000/- sanctioned by Board. Revised estimate(1524W/2011) of ` 6.55 Cr was sent to finance for vetting on 11.07.2011. Finance raised certain observation dated 18.10.2011 which is under compliance. Observation compiled and resubmitted to finance for vetting on 01.02.2012.
34 | 42 | RNC-Platform no.4&5. | 11.04 | 0.4 | Detailed Estimate bearing no. 1373W/2008 sanctioned 01.09.08.
35 | 43 | BBN-Development of goods shed as a freight terminal. | 11.9269 | #REF! | Detailed Estimate bearing no.1405W/2009 costing to `11,92,98,164/- sanctioned by CAO(C )/GRC on 09.06.2009.
36 | 45 | Ramgarh Town - Yard remodelling, Mael - 2-nd loop, Barkipona - Addl loop & Hanubera - 2nd loop | 17.0778 |  | Detailed Estimate bearing no. 1416W/2009 of `18,24,07,570/- sanctioned by CE/C/II/GRC. Revised estimate bearing no 1560W/2012 of ` 22,36,64,702/- sanctioned by CE(C )II/GRC vide this office letter No PD/W/710/1/2391 dated 07.06.2012.
37 | 47 | DPS - B.P line(RKSN) | 15.13 | 2.84 | Detailed Estimate no.1324W/2006 sanctioned on 31.01.06 .
|  | Material Modification for underpass | 0.62 |  | MM Estimate No.1397W/2009 for 2 Nos. Minor bridges has been prepared as per local demand & as per instruction of GM.GM sanctioned the estimate on 25.03.2009.
38 | 50 | KGP - Bhadrak - Addl. Loops in down direction | 18.37 |  | Detailed estimate bearing no 1471W/2010 of `29,99,33,158/- sanctioned by CAO/C/GRC on 20.12.2010.
39 | 51 | JSG-Development of goods shed as a freight terminal. | 5.72 | #REF! | Detailed Estimate estimate bearing No 1521W/2011 of ` 9.65 Cr sanctioned by CE/C/I/GRC vide letter no.PD/W/702/1/3156 dt. 12.08.2011.
40 | 52 | NOMD-Development of goods shed as a freight terminal. | 2.53 | #REF! | Detailed Estimate bearing no. 1404W/2009 costing to `3,68,32,710/- sanctioned by CE(C )S/GRC on 22.10.2009.
41 | 53 | Tatanagar Goods departure yard - Development of freight terminal | 10.19 |  | Detailed Estimate bearing No. 1439W/2009 costing to `10,19,25,179/- sanctioned by CE(C )I/GRC on 29.12.2009.
42 | 55 | Illoo - Addl. Loop line | 4.2063 |  | Detailed Estimate bearing no.1415W/2009 of `4,24,53,158/- sanctioned by Dy.CE/C/P&D/GRC.
43 | 57 | Rangra - Hot axle siding | 5.29 | 0.2 | Detailed Estimate no.1366W/2008 costing `5.29 Cr. Sanctioned on 26.05.08.
44 | 58 | Kastur - Addl. Loop facility with central panel | 7.96 |  | Detailed Estimate bearing No. 1427W/2009 Costing to `7,95,69,436/- sanctioned by CE/C/II/GRC.
45 | 59 | Urma - Addl loop facility with central panel | 7.69 |  | Detailed Estimate bearing No.1426W/2009 Costing to `7,69,13,102/- sanctioned by CE/C/II/GRC.
46 | 61 | Sonamukhi & Bhowaichandi - Crossing station with 2 loops each | 33.6289 |  | Detailed estimate bearing No 1459W/2010 of `33,62,89,400/- sanctioned on 19.11.2010.
47 | 63 | KRMD - two loading lines | 5.26 | 1.49 | Detailed Estimate no.1349W/2007 sanctioned on 17.12.07.
48 | 66 | Santragachi - Development of circulating area (2011-12) | 198.65 |  | Part estimate bearing no. 1528W/2011 of ` 3,66,25,906/- sanctioned by CAO/C/GRC on 09.09.2011.Another part estimate bearing no. 1547 W/2012 of `23.8 crores for essential passenger ammenities work vetted by finance. Estimate kept pending as work is being awarded to IRCON.
49 | 67 | Shalimar - Development of coaching terminal(2011-12) | 192.44 |  | Part estimate bearing no. 1542 W/2012 of `68.12 crores submitted to Railway board on 4/4/12 for sanction.
50 | 68 | Hijli - Addl dock platform(2011-12) | 10.65 |  | New works. Plan & Estimate under preparation. Detailed estimate bearing no. 1549 W/2012 of `13 crores under finance vetting since 08.5.12.
51 | 69 | Sankrail - Freight terminal | 113.3 |  | Detailed estimate bearing no.1534 W/2011 of `147.35 crores submitted to Railway Board on 4/4/12.
52 | 70 | Sankrail-Santragachi - Link line (14.5 km) via flyover (2011-12) | 203.79 |  | Part estimate(1503W/2011) of ` 72,06,700/- sanctioned by CAO/C/GRC on 06.07.2011. Detailed estimate bearing no. 1544 W/2012 of ` 236.93 crores submitted to Railway Board on 4/4/12.
30 ROB/RUB
53 | 90 | Andul-Sankrail - ROB(11-12) | 14.05 |  | Combined GAD has not yet finalized by CBE. ROB proper portion GAD finalized. Dy.CE/C/KGP, CEE/C/GRC & CSTE/GRC have been asked to submit the detailed estimate based on GAD of ROB proper portion.
54 | 91 | Soro - ROB(11-12) | 10.45 |  | Part estimate bearing no 1505 W/2011 of `5.62 crores sanctioned vide this office letter no. PD/W/774/4324 dated 14/11/11. Combined estimate prepared just after submission of estimate of approaches by State Govt and send to Railway Board for sanction on 08.6.12.
55 | 92 | Bankura-Chhatna - ROB(11-12) | 18.57 |  | GAD has not yet finalized by CBE. Estimate will be prepared after approval of GAD.
56 | 93 | Urma-Barabhum - ROB(11-12) | 18.6
57 | 94 | Kolaghat-Bagnan - ROB 35 (11-12) | 14.05
58 | 95 | Kharagpur-Gokulpur - ROB(11-12) | 28.63
59 | 96 | Nalpur-Bauria - ROB(11-12) | 18.6
60 | 97 | Jhalda-Kotsila - ROB(11-12) | 17.85
61 | 98 | Jhalda-Kotsila - ROB(11-12) | 17.85
62 | 99 | Purulia-Gourinathdham - ROB(11-12) | 17.75
63 | 100 | Bagnan - ROB | 8.29 | 2.5 | Detailed Estimate no.1241W/2002 sanctioned on 09.04.03. Revised estimate is being prepared after submission of latest estimate by State Govt.
64 | 101 | BCK-ROB | 7.74 | 2.5 | Detailed Estimate no 1464W/2010 of ` 42,78,62,785/-(Rly's share: ` 14,83,50,512/- & State Govt's share: ` 27,95,12,273/-) sanctioned by AGM/SER vide this office letter dated 15.04.2011.
65 | 102 | JGM -ROB | 6.07 | 2 | Detailed estimate bearing no.1431W/2009 of `12,84,86,652/- as accepted by State Govt has been sanctioned on 12.08.2010.
66 | 103 | RNC-NKM ROB | 15.35 | 3 | Estimate accepted by State Govt.
67 | 105 | ROU-ROB | 9.74 | 3 | Detailed estimate No. 1384W/2008 costing to `15.77 Crores sanctioned on 30.01.09. Estimate of approaches received on 31.01.2012. Dy.CEE/C/ROU & CSTE/C/GRC asked for submission of estimate.
68 | 106 | Bhadulmore-ROB | 6.9 | 0.01 | Detailed estimate bearing no. 1406W/2009 of `44,10,86,160/- sanction by AGM on 25.08.2010.
69 | 107 | Jhantipahari - Chhatna - Road over bridge in lieu of existing one | 4.518 |  | Detailed Estimate bearing No. 1425W/2009 of `4,51,80,100/- sanctioned by Dy CE(C )P&D/GRC on 14.01.2010.
70 | 108 | Ulberia - Birshibpur - ROB | 23.62 |  | Detailed estimate bearing No 1460W/2010 of `22,43,38,696/- sanctioned by CAO(C )GRC on 13.10.2010.
71 | LB | Mahuda - Jamuniatand ROB | 1.68 |  | Detailed estimate of Civil Engg. Portion submitted. State Govt submitted approaches on 06.10.2010. Detailed Estimate bearing no.1483W/2010 of `4,40,28,276/-(Rly's share: `2,20,14,138/-& State Govt's share: `2,20,14,138/-) sanctioned by CAO/C/GRC on 09.09.2011.
72 | LB | CKP - ROB | 1.99 |  | Detailed estimate bearing No 1267W/2003 of `4.05 (1.99 + 2.06 ) cr sanctioned on 07.08.2001.
73 |  | RNC-Hatia ROB (Mecon Colony) | 15.26 |  | Detailed estimate bearing. 1478W/2010 of `22.04 crore vetted by finance and sent to State Govt. for their acceptance on 04.02.2011. State Govt advised to change the scope from 'Y' leg to Road diversion.Accordingly work has been dropped from pink book 12-13.
74 |  | GTS -ROB | 5.25 | 0.01 | Detailed Estimate no.1250W/2002 sanctioned 11.06.03.
75 |  | Rangamati - ROB | 6.11 | 2 | Detailed Estimate no.1256W/2003 sanctioned 04.07.03.
32 Bridge
76 | 300 | Br.no.412 | 9.88 | 9.75 | Detailed Estimate bearing No. 1302W/2005 of `6.28 crore sanctioned by CBE/GRC. Revised Estimate no.1325W/2003 sanctioned on 17.08.06.
77 | 313 | Howrah - Kharagpur Metalising of trangulation spans (Br No 57)(11-12) | 4.81 |  | Estimate is under preperation.
42 Workshop
78 | 404 | Shalimar - Two pit lines with catwalk (11-12) | 10 |  | Detailed estimate bearing no.1545 W/2012 of `12.49 crores is under finance vetting since 05.4.12.
79 | 405 | Padmapukur - Coaching facilities(11-12) | 31.5 |  | Detailed estimate bearing no. 1533W/2011 costing ` 37.78 Crore sanctioned by CAO/C/GRC vide letter no. PD/W/786/0021 DATED 02/01/2012.
80 | 408 | BKSC-ELS | 43 | 1.67 | Detailed Estimate No. 1181W/1997 of `22.36 crore sanctioned by Board on 15.10.1998.Revised Estimate no.1335W/2006 of `43.00 Cr. sanctioned by Board on 06.05.2008.
81 | 410 | TATA - Coaching maintenance | 23.8754 | 3 | Estimate no.1333W/2006 sanctioned on 10.09.07. Revised estimate bearing No 1473W/2010 of ` 23,87,53,984/- sanctioned by CE(C )S/GRC as communicated vide letter No PD/W/699/1/0925 dated 09.03.2011. 2nd revised estimate as submitted by CEE/C/GRC is under consideration.
82 | 411 | Hatia(Coaching Depot)- IWC | 13.51 |  | Detailed estimate bearing no. 1454W/2010 of ` 19,77,48,321/- sanctioned by CE/C/II/GRC vide this office letter dated 20.04.2011.
83 | 412 | NMP-Upgradation | 6.32 | 2 | Detailed Estimate no.1330W/2006 sanctioned 17.07.06. Revised estimate bearing no. 1501W/2011 costing ` 13.62 Crore sent to finance vetting. Finance raised certain observation vide letter dated 22.07.2011 which is under compliance. Estiamte resubmitted on 23.01.2012 for finance vetting. Finance against raised observation and returned on 31.01.2012. Mechanical department sent their compliance on 08.02.2012.
84 | 413 | Adityapur - New routine overhauling shed for air brake stock | 11.34 |  | Detailed estimate bearing no 1438W/2009 of `11,33,73,897/- sanctioned on 06.05.2010.
85 | 414 | Bokaro Steel City - Extension of routine overhauling depot for maintenance of block rake with covered shed | 12.7799 |  | Detailed Estimate No. 1434W/2009 of `12,77,99,795/- sanctioned by CE/C/II/GRC.
86 | 415 | SRC-ELS | 1.94 | 0.7 | Detailed Estimate no.1320W/2006 sanctioned on 22.03.07.
87 | 416 | Bokarao Steel City - Upgradation of premium rake examination facilities at empty yard. | 5.3602 |  | Detailed Estimate bearing No. 1432W/2009 of `5,36,02,099/- sanctioned by CE/C/II/GRC on 26.02.2010.
88 | 417 | Bhojudih - Augmentation of sick line facilities at carriage & wagon examination point | 5.59 |  | Detailed Estimate No 1447W/2010 of `7,90,26,214/- sanctioned on 17.06.2010.
89 | 418 | Bondamunda (ELS) - Extension at Chakradhapur end by 28.5 m to increase loco holding to 175 | 10.2215 |  | Detailed Estimate bearing No. 1424W/2009 of `10,22,15,251/-sanctioned by CE(C )I/GRC on 05.02.2010.
90 | 419 | TATA-Cover shed | 8.55 | 3 | Detailed Estimate no.1308W/2005 of `8,55,44,313/- sanctioned on 19.05.06. Revised estimate bearing No.1453W/2010 of `13,15,63,017/- sanctioned by CE(C )South on 31.08.2010.
91 | 420 | BNDM - Medium sick line | 7 | 2 | Detailed Estimate no.1346W/2007 sanctioned on 24.09.07.Revised estimate bearing No.1442W/2010 of `7,00,32,172/- sanctioned.
92 | 421 | Tatanagar - Extension of wheel shop at centralised traction repair centre | 5.9514 |  | Detailed Estimate bearing No. 1429W/2009 sanctioned by CE/C/I/GRC on 18.12.09.
93 | 422 | Bokaro - Augmentation of old sick line with EOT crane facility | 10.4863 |  | Detailed Estimate bearing No. 1435W/2009 of `10,48,62,895/- sanctioned by CE/C/II/GRC on 26.02.2010.
94 | 423 | ADTP - Sick line | 3.16 | 1.01 | Estimate no.1304W/2005 sanctioned on 16.05.06.
95 | 424 | Tatanagar -ELS | 9.6701 |  | Detailed estimate bearing No 1466W/2010 of ` 9,67,01,198/- sanctioned by CE(C )South/GRC as communicated vide letter No PD/W/753/0945 dated 09.03.2011.
96 | 425 | TPKR - Extension of inspection/stabling pits | 4.04 |  | Detailed estimate bearing no. 1517W/2011 of ` 6,39,27,065/- sanctioned by CE(C )HQ/GRC vide letter No PD/W/751/ dated 10.06.2011.
97 | 426 | Kharagpur - Excellence for wagon pro-typing centre. | 100.17 |  | Detailed estimate bearing no. 1518W/2011 of `102.28 Crore sanctioned by Board vide letter no. 2011/M/W/964/65 dated 13/02/2012.
98 | 428 | SRC - IOH | 6.01 | 0.91 | Detailed Estimate no.1232W/2001 sanctioned on 10.07.01. Revised estimate (1440W/2009) of `13,18,10,952/- sanctioned by CE(C)HQ/GRC on 22.07.2010.
99 | 429 | Padmapukur - Coaching maintenance | 11.75 | 0.05 | Detailed Estimate No. 1367W/2008 sanctioned on 01.09.08. MM Estimate bearing No 1443W/2010 of ` 41,14,493/- for S&T works sanctioned on 09.04.2010.
100 | 431 | Dangoaposi - Augm. of sick line maintenance facilities (12-13), (DF-3) |  |  | Detailed estimate is under preparation.
101 | 432 | Bondamunda - Second ELS to home 200 electric locos(12-13), (CAP)
102 | 433 | Rourkela - Extension of washing pit line to cater 26-coach length trains 12-13), (DF-3)
103 | 434 | TATA, BKSC & HTE - Satellite depots for maintenance of track machines (12-13), (DF-3)
104 | DW | BNDM-ROH | 6.6 | 1.11 | Estimate no.1306W/2005 of `6.60 crore sanctioned on 16.05.06. Due to increase in cost Revised estimate bearing No. 1394W/2009 of `9,32,79,332/- sanctioned by CE/C-I/GRC.
105 | DW | KGP - EMU Car shed | 14.31 | 1.11 | Detailed Estimate bearing no. 1187W/1997 of `9.99 crore sanctioned on 28.05.98. Revised Estimate no.1254W/2002 sanctioned on 11.07.03.
51 Staff Quarters
106 | 437 | Dongaposi - Type-II 63 units & type-III-12 units | 5.4665 |  | Detailed Estimated bearing No.1417W/2009 sanctioned by CE/C/South/GRC on 14.12.2009.
107 | 438 | Dongaposi - Type-II 60 units | 4.5727 |  | Detailed Estimated bearing No.1430W/2009 sanctioned by Dy.CE/C/W/GRC on 14.11.2009.
108 | 439 | ADA-70 units type II &15 units type III | 7.88 | 0.1 | Detailed estimate bearing no. 1377W/2008 of `7,87,77,230/- sanctioned by CE/C/II/GRC on 03.08.2009.
109 | 440 | Adra - Repl. Of quarters, type-II-93 units at North settlement | 5.7557 |  | Detailed Estimated bearing No.1412W/2009 sanctioned by CE/C/II/GRC on 24.09.09.
110 | 441 | Adra - Repl. Of quarters, type-II-93 units at East settlement | 5.7557 |  | Detailed Estimate bearing No.1410W/2009 sanctioned by CE/C/II/GRC on 24.09.2009.
111 | 442 | Adra - Repl. Of quarters, type-II-93 units at South settlement | 5.7557 |  | Detailed Estimate bearing No.1411W/2009 sanctioned by CE/C/II/GRC on 24.09.09.
112 | 443 | Anara - Repl. Of quarters, type-II-69 & type-III -15 units | 5.4872 |  | Detailed Estimate bearing No.1409W/2009 sanctioned by CE/C/II/GRC on 24.09.09.
113 | 444 | Adra - Repl. Of quarters, type-II-58 units at Seva Nagar colony | 5.3259 |  | Detailed Estimate bearing No. 1413W/2009 sanctioned by CE/CON/II/GRC on 24.09.09.
114 | 445 | BKSC - Type-II-50, Type-III-25, Type-IV-4 & Type-V-1 unit | 5.18 |  | Detailed estimate bearing No 1457W/2010 of `7,80,14,508/- sanctioned on 09.07.2010.
52 Staff Amenities
115 | 448 | Nurshing Collage at GRC | 26.26 |  | Soil investigation completed. Plan & estimate under preparation.
116 | 450 | KGP-Water treatment plant | 6.82 | 2.04 | Revised estimate no.1305W/2005 sanctioned on 22.12.05.
117 | 452 | RNC- 50 Bedded Hospital | 4.17 | 1.6 | Detailed Estimate no.1344W/2007 sanctioned on 12.03.08. 2nd reminder sent to CEE/C/GRC, CSTE/C/GRC & CMD/GRC for submitting revised estimate on 24.01.2012 and 3rd reminder sent on 03.02.2012. Electrical and S&T sub-estimate received on 13.02.2012. Medical department is still awaited.
118 | 453 | RNC- Astrotuf | 5.22 | 0.4 | Detailed estimate bearing no. 1374W/2008 sanctioned on 11.08.08.
119 | 454 | Chakradharpur - Upgradation of divisional hospital | 5.6934 |  | Detailed estimate1433W/2009 Costing to `5,87,05,557/- sanctioned by CE(C )I/GRC on 14.06.2010.
120 | 455 | Adra Division - Reinforced concrete cement overhead tanks for improved water supply. | 5.7557 |  | Detailed Estimate bearing No. 1412W/2009 sanctioned by CE/C/II/GRC on 06.10.2009.
121 | 458 | RNC-HTE Water Supply. | 4.5257 |  | Detailed estimate bearing no. 1475W/2010 of `4.08 crore sanctioned on 04.02.2011.
122 | LB | Nurshing Collage at GRC | 0.9967 |  | Detailed estimate bearing No 1477W/2010 of `99,73,518/- sanctioned by Dy CE (C )II/GRC on 16.09.2010.
53 Passenger Amenities
123 | 462 | KGP - Platform shelter (1,2,3/4 & 5/6) |  |  | Detailed estimate bearing No 1470W/2010 of `5,68,78,003/- ( Civil Engg only ) sanctioned by CE/C/HQ/GRC on 13.10.2010. MM Estimate bearing no. 1515W/2011 of ` 28,18,653/- for electrification of shelter sanctioned on 20.05.2011.
124 | 466 | HTE-Platform shelter |  |  | Detailed estimate bearing 1445W/2010 costing `6,82,73,944/- sanctioned by CE(C )II/GRC as communicated vide letter no PD/W/757/0502 dated 04.02.2011.
125 | 469 | Hijli - Station building & circulating area(11-12) | 17.98 |  | Detailed estimate bearing no. 1550 W/2012 of `21.06 crores is under finance vetting since 03.05.12.
126 | LB | Digha- Washable apron on Line no. 1. | 0.851 |  | Detailed estmate of `1,26,58,886/- bearing No 1451W/2010 sanctioned by Dy. CE(S& C)GRC.
64 Other Specified works
127 | 474 | TATA -200 bedded hostel | 3.1 | 2.57 | Detailed Estimate no.1345W/2007 sanctioned on 23.07.07.
128 | 476 | SINI - Zonal Training institute | 5.35 | 2 | Detailed estimate bearing no. 1368W/2008 sanctioned on 04.09.08.
129 | 477 | Tatanagar (Electrical Loco Training Centre) - 200 beded new hostel building (2nd wing) | 6.8404 |  | Detailed Estimate bearing no. 1422W/2009 Costing to `6,84,03,926/- (59.73% over PB cost) sanctioned by CE/C/I on 30.12.09.
130 | 478 | Kharagpur-Advanced railway loco pilot training centre. |  |  | Part Estmate bearing No 1467W/2010 of `22,25,597/- sanctioned on 12.08.2010. Detailed estimate bearing no. 1530W/2011 of ` 19.27 crores sanctioned by Railway Board on 23.05.12.
0100 Deposit
131 |  | Karkend | 0.9629 |  | Detailed Estimate No1037W/1989 of `28.5 lakh sanctioned on 07.01.1999. Revised Estimate No1209W/1999 of `96.29 lakh sanctioned on 30.06.03. 2nd Revised Estimate bearing No 1316W/2005 of `131.62lakhs prepared and sent to State Govt. for their acceptance.
132 |  | MCL - Siding | 469.68 | 67.15 | Detailed Estimate no. 1372W/2008 costing `469.33 Crores sanctioned. Revised estimate is pending for S&T sub-estimate. 2nd reminder sent to CSTE/C/GRC on 30.01.2012.
133 | - | Subarnrekha -Canal crossing in between ROP and BPO. | 2.26 | 1.11 | Detailed estimate sanctioned without provision of diversion/RS girder as the line was under commissioned. Revised estimate No.1392W/2008 has been prepared and sent State Govt. accepted the estimate. Sanction of CAO/C obtained on 22/04/2009.
134 | - | Subarnarekha -Canal crossing in between BPO-BGY. | 2.26 | 0.018 | Detailed estimate NO 1387W/2008 has been prepared and sent State Govt. for acceptance after finance vetting on18.02.2009.They accepted the Estimate on 03.03.2009 and deposited full amount of Estimate. Sanction of CAO/C obtained on 28/04/2009..
135 | - | Shifting the connection of mid-section OMDC/EIML Siding for Barbil - Barajamda doubling. | 0.75746 |  | Detailed estimate bearing no 1484W/2010 costing ` 75,74,588/- sanctioned by Dy.CE/C/P&D/GRC.
136 |  | Shifting of TK-1 in BBN - BJMD for OMDC siding |  |  | Detailed estimate of bearing no. 1458W/2010 of ` 99,84,099/- sanctioned by Dy.CE/C/P&D/GRC